## Sheet1
Project Timeline
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27
Develop project design, write project plan
Develop questionnaire
[7 empty] | Program, test questionnaire | [8 empty] | Lock and load machines
Develop sample mgmt system
[8 empty] | Program, test sample management system | [7 empty] | Lock and load machines
Write project manual
IRB Review
[14 empty] | Develop training matls |  |  | Assemble trng matls
[18 empty] | Final training prep | TL Training | Iwer Training
Production interviewing