SRO documentation – revised July 5, 2011

(Initial communication -- October 2004)

# Time Table for Staffing/Laptop Loading

Getting staffing and equipment needs specified early in pre-production will increase the likelihood for a successful launch of a survey project using laptop equipment.

With input from DCS, TSG and DCO, we are offering the following guidelines:

| TIME – weeks before training | TASK |
| --- | --- |
| 12+ weeks | Confirm training site/locations |
| 12 weeks | Give base estimate for number of iwers (new hire and on-staffers). [DCO will estimate incremental laptops that may be needed.] |
| 8 weeks | Update iwer and laptop counts [Laptop procurement] |
| 4-6 weeks | Update iwer and laptop counts – confirm. New laptops ordered if necessary. |
| 2 weeks | Staffing list frozen / laptops loaded Tenrox set up forms to DCO-DCS |
| 0 week | Training launch |

Other noteworthy items:

- Please contact the DCO Training group early to confirm training site requirements.  (Ashanti and Beth are happy to meet your every need!)

  - Project trainings lasting on 1-3 days typically require 3 months lead time for site selection and confirmation (contract signature).

  - Project training lasting 3+ days typically require 6 months lead time for site selection and confirmation.

    - “Its never too early to plan for site selection.”

- Mike Etzel updates the SRC total laptop usage charts each month and provides input to SRO Operations.   He coordinates laptop purchases for SRO.

  - The Production Manager or other responsible team member will need to explicitly coordinate hardware allocation with Mike.

- Regardless of the number of new hires, TSG has requested a two week window between the time the staffing lists are “frozen” and the start of training.  The cross-project coordination for hardware usage warrants this timing.

- The TSG staff use the Eroom information exchange for updates on the staffing tables for specific projects.  (See document: Interviewer Staff List - Location and Maintenance Procedures for details.)

- Field staffing assignments are made by production managers in accordance with the DCO Contingent Staff Assignment policies. The DCO Manager will review all staffing plans before interviewers and TLs are approached, and assigned to a project.  If cross-assignments are going to be necessary, this must be vetted through the Board of PIs.  The DCO Manager will coordinate this step with the project leaders and the Board.

- Typically, if an interviewer will  not be active for more than 4 weeks, the laptop should be returned to SRO.

  - Questions about this procedure should be directed to Jody Dougherty, Vivienne Outlaw, or Mike Etzel.