HRS 2010

Team Leader Project Manual

Institute for Social Research

University of Michigan

Table of Contents

Chapter 1: Purpose and Background	1

1.1:  Study Purposes and Background	1

1.2:  Ancillary Studies and Off-Year Communication	2

1.3:  New Components for 2008	3

Chapter 2:  Team Structure	5

2.1:  Team Structure	5

Chapter 3:  Production Management	11

3.1:  Sample Management	11

3.2:  Production Goals	12

3.3:  Handling Performance Concerns	13

3.4:   Documentation (Employee Activity Report)	16

3.5:   Reporting Illness/Injury/Theft or Adverse Events	16

3.6:   Clinical Contact Portal	16

3.7:  Team Meetings	20

3.8:  Team Production Reports	20

3.9:  National Tracking Team (NTT)	21

3.10:  WebTrak (WT)	21

3.11:  Dynamic Production Management (DPM)	22

3.12:  eRoom	23

3.13:  Staff Lists/Updates	24

3.14:  Interviewer Travel	24

3.15:  Performance Assessment Form (PAF)	25

3.16:  Approving Time and Expenses in Tenrox	25

3.17:  Interviewer Supplies	27

Chapter 4:  Project Supervision	29

4.1:  Interview Mode	29

4.2:  Proxy Interviews	29

4.4.:  Respondent Types (Change Requests)	30

4.5:  Respondent Profiles	30

4.6:  Rules for Removing from Sample	31

4.7:  Call Records/Result codes	32

4.8:  Sample Transfers	32

4.9:  Quality Plan	33

4.10:  HRS Q&A	35

4.11:  Post Production Activities	36

Appendix A:	37

Employee Commitment Statements	39

Employment Commitment Statement	41

Employment Commitment Statement	45

New Hires	45

Employment Commitment Statement	49

Bilingual	49

Employment Commitment Statement	53

New Hires-Bilingual	53

Report Charts	57

Text Report Template	59

Adverse Event Fact Sheet	63

Illness/Injury/Incident Report	66

Tenrox Instructions	71

Tenrox Work Type Definitions	73

Laptop Return Instructions	75

Interview Certification Forms	79

HRS 2008 Interview (Application) Certification	81

HRS 2008 Interview (Application) Certification	83

Appendix B: WebTrak Manual	87

Chapter 1: Purpose and Background

## 1.1:  Study Purposes and Background

America’s demographic profile is undergoing a dramatic change.  Over the next several decades, lengthening life spans combined with the aging of the population bulge-those born during the “baby boom” years of 1946-1965- will transform us from a youthful society to a middle-aged and elderly society.  The magnitude of the “new age America” will impose major new challenges to the nation’s health and economic institutions.

The Health and Retirement Study (HRS) was designed to provide academic researchers, policy analysts and program managers with reliable, current data on the economic and physical well-being of men and women 50 years of age and older in America.  In addition, it was intended to furnish insight into how, over time, health and wealth interact with work, retirement and family responsibilities to affect the decisions that they make.

In 1992, the Survey Research Center (SRC) launched the largest data collection effort in its history.  The HRS was viewed as one of the most valuable and innovative studies ever undertaken to better understand how people fare as they age.

Based on 1990 U.S. Census data, approximately 70,000 households in the U.S. were selected for screening and possible inclusion in the study.  Initially, it was decided the HRS would focus on people who were close to retirement.  The eligible respondents were, therefore chosen from a single birth cohort (or group of people born within the same span of years), in this case, people born between 1931 and 1941 and their spouses or partners.  The year 2010 will mark the 10th wave of HRS interviews.

The HRS sample consists of birth cohorts nationally representative of people in the U.S. aged 50 years and older.  The HRS is currently comprised of approximately 20,000 respondents and is planned to be a long-term longitudinal project.  In order to ensure the sample remains representative of this population it is necessary to supplement the sample with an additional, younger birth cohort every six years.  This allows researchers to track trends as people move from work into retirement and beyond.

The HRS 2010 sample contains the following birth cohorts:

- The AHEAD (Study of Asset and Health Dynamics) cohort is the oldest population in the sample.  These respondents represent people in the population who were born in 1923 or earlier.

- The “Children of Depression Age” (CODA) cohort is a sample of people born between 1924 and 1930 and their spouses or partners if born in the same time period or after January 1, 1948.  This sample comes from the Health Care Financing Administration (HCFA) database.  The year 2010 will mark the seventh wave of interviews with CODA respondents. Normally, the HRS sample is only supplemented at the younger end every six years; however, people in this cohort had been under-represented in the sample.  As a result, the sample in this group needed to be increased and was added in 1998.

- The HRS cohort comes next.  These respondents represent people who were born between 1931 and 1941.

- The “War Baby” (WB) cohort, pre-screened in 1992, is a sample of people born between 1942 and 1947 and their spouses or partners.  The year 2010 will mark the seventh wave of interviews with WB respondents.

- The “Early Baby Boomer” (EBB) cohort screened in 2004.  This cohort represents those born between 1948 and 1953.  38,385 lines were screened in order to produce 3,340 interviews with people in the EBB age range.

- The “Mid Baby Boomer” (MBB) cohort, those born between 1954 and 1959. These respondents will be interviewed for the first time during this 2010 wave of data collection.  In addition to the respondents who were screened into this cohort during the 2004 wave, a supplemental screening will be completed in 2010 to identify approximately 4,000 additional eligible respondents.

## 1.2:  Ancillary Studies and Off-Year Communication

Over the last few years, several ancillary studies have been completed using portions of the HRS respondent panel.  Most of these studies, including the Off-Year Mail Out and Diabetes studies, were completed in order to augment data collected as part of the core HRS.  ADAMS and the Internet Study allowed researchers to explore a particular topic in greater detail than would have been possible within the context of core data collection.  In 2003, we completed an Estate Callback effort to collect missing data. The Prescription Drug Study (PDS) is a mixed-mode survey initiated in 2005 and was repeated in 2007 with the same respondents.  In 2009, a similar survey was administered; which is called “The Health and Well-Being  Study (HWB)”and is part of the Health and Retirement Study (HRS) umbrella of studies.  This was the first wave of this particular mail survey, which includes sections from the Prescription Drug Study of 2005 and 2007, and an additional section on well-being.  HWB was carried out in the fall of 2009 and consisted of approximately 7,417 HRS respondents.  The purpose of this effort is to collect additional data on prescription drug use, coverage, cost, and satisfaction from participants in the HRS, as well as collect data on their self-reported well-being.

The HRS project manual contains additional information on the recent ancillary studies, including ADAMS, the Internet study, the third wave of CAMS, the second wave of PDS, the first wave of HWB and the first wave of the Disability Vignettes Study (DVS).

In addition, newsletters are sent to our panel members periodically in order to keep them abreast of study happenings.  The last HRS newsletter was mailed to respondents by interviewers in the precontact letter.  A 2010 version is in development for release later this year.

The HRS 2010 Respondent Profiles indicate whether or not each respondent was a member of any of the ancillary studies, the year of his or her inclusion and whether or not contact was achieved.

## 1.3:  New Components for 2010

Although the HRS is a longitudinal, panel study, there are always new and interesting additions to data collection each wave. Some of the new features are described below.

- A new quality control system is in place which allows us to digitally record interviews without using a tape recorder. This eliminates the need to use a tape recorder and should be a seamless process for the Interviewer.  On a weekly basis, Interviewers will copy the files onto a CD and mail the CD to Ann Arbor for evaluation.

- Another new component for 2010 data collection will be the confirmation process for those who screened in as eligible MBBs in 2004. This will involve a separate Blaise instrument in its’ own SurveyTrak directory.

- Given the size and scope of the data collection efforts required this wave, the field staff will be divided into two distinct teams. The Screening Team will focus solely on the screening effort of approximately 17,500 lines. They will later be trained on the main interview (just prior to the mid-study workshop).  The Main Team will focus solely on MBB confirmations and completing the interviews with panel and newly identified EBB and MBB respondents

Chapter 2:  Team Structure

## 2.1:  Team Structure

We’ll have three Production Coordinators and 14 Team Leaders on the Main Team with one Production Coordinator and six Team Leaders on the Screening Team.. Dianne Casey, along with Sarah Crane, will oversee production and will work directly with the Production Coordinators.

The table below outlines the major areas of responsibility by role.

| Accountability | Interviewer | Team Leader (TL) | Production Coordinator (PC) |
| --- | --- | --- | --- |
| Communication: Skills and levels of communication. | Communicates mainly with Team Leader for routine issues (via email and telephone) Participates in conference calls. | Maintains close (and scheduled) communication with interviewers an PC Co-facilitates interviewer CCs on a weekly basis Guides assigned interviewers on strategies to improve performance Shares interview evaluation feedback with assigned interviewers | Maintains on-going direct communication with Production and Project Managers Communicates information to TLs using high level skills including negotiation, coaching, mentoring and presentation. Develops agendas and facilitates conference calls, including training calls as required. Provide feedback and problem-solve with all levels of the team, including the Project Manager(s). Utilize advanced skills in report writing and correspondences Prepare and present training materials as required Maintain eRoom files throughout data collection |
| Knowledge: What is known and how it’s used. | Understands and implements GIT skills Understands and implements the HRS protocols. Utilizes the provided reference manuals and seek further knowledge as required. Utilizes a basic understanding of Email and Microsoft Office programs. | Understands and implements basic leadership skills to effectively guide assigned data collection teams to complete daily production tasks as presented at TL training | Understands and implements advanced leadership skills Recognizes and utilizes the formal organizational structure in daily communication Display the ability to lead 5 small teams simultaneously Prioritize and coordinate tasks between teams to meet daily production tasks and goals Understands and utilizes Microsoft software programs (Outlook Express, Word and Excel), and assist team members in the use of these programs |
| Quality Control: QC tasks and expectations. | Maintains security and confidentiality of all data Responsible for completing interviews and collecting other research data using standard SRC principles, procedures, and protocols. | Responsible for monitoring the quality of work completed by a team of interviewers and reporting on deviations from SRC standards Responsible for monitoring all production reports provided in WebTrak and/or eRoom | Responsible for monitoring the quality of work completed by a large work group or group of teams and reporting on deviations from SRC standards. Responsible for training, mentoring and assisting the Team Leaders in their work group with QC tasks and reporting on their competency completing QC tasks. |
| Production: Data collection activities and level of responsibility. | Responsible for completing interviews and collecting data, as assigned Responsible for achieving the interviewer production and efficiency goals set by the study. | Work with interviewers to develop effective refusal aversion/conversion strategies. Responsible for monitoring and reporting on the work completed by a team of interviewers and help to further develop their skills. Responsible for providing input to the Production Coordinator on Interviewer performance during the Iwer PAF periods Responsible for achieving the team production and efficiency goals set by the study. | Responsible for broad oversight of TL and their teams. Responsible for submitting detailed work group production reports to a Production Manager on a scheduled basis Responsible for providing input on development and implementation of data collection and reporting procedures Responsible for providing input to the Production Manager on Team Leaders as well as Iwer performance during the Iwer/TL evaluation periods throughout data collection Responsible for facilitating sample distribution and work flow within the work groups. Responsible for training, mentoring and assisting other Team Leaders in their work group with production tasks and reporting on their competency completing production tasks . |
| Team Function: How each group fits into the larger organization | Contributes and participates in team activities as a productive member of the team. Functional oversight provided by a Team Leader in conjunction with a Production Coordinator and Production Manager | Model professional behavior and adherence to SRC standards. Functional oversight provided by a Production Coordinator in conjunction with a Production Manager. | Lead and coordinate data collection team activities Functional and administrative supervision provided by Production Manager |

Each Production Coordinator will be assigned Team Leaders (TLs)and will report directly to a Production Manager.  Team Leaders will work with 8-12 interviewers including both on-staff and newly hired interviewers.  TLs will report to their assigned Production Coordinator. (See org. chart in Appendix ???)

Dianne Casey will serve as the Lead Production Manager and will work in partnership with Sarah Crane who will directly oversee the Screening Team.  While Dianne’s main focus will be on the Main Interviewing Team and Sarah’s focus on the Screening Team, working together and staying in close communication will be crucial to the success of data collection. Efforts on both teams impact the other.  Sarah and Dianne will work directly with the PCs on a daily basis and will be responsible for coordinating field efforts in meeting the overall data collection goals. Additionally, they will act as the liaisons with Ann Arbor on all data collection issues.

National Tracking Team (NTT)

The tracking team will consist of eight members of the field staff led by Jude Griswold, an HRS TLC. All members will have WebTrak access and will be responsible for guiding their assigned interviewers through the HRS tracking steps. Refer to Chapter 7 for NTT role and responsibility details.

The members are listed below:

- Patricia Contreras

- Lori Curtis

- Joan Harriss

- Maggie Knowles

- Kathy Lavender

- Patricia Longoria

- Stuart Shore

- Cecilia Waguespack

Management Team

Each project/production manager is responsible for providing support to the field staff.  In addition, each will focus on either the New Sample or the Panel side of the project as indicated below.

Heidi Guyer:          Overall HRS Study Management

Jennifer Arrieta:     New Sample Project Management

Baseline Iw after July

Maryam Buageila: New Sample Project Management

Ancillary Studies

Sarah Crane:          New Sample Production Management

QC

Dianne Casey:            Panel Sample Production Management

Overall production management

Andrea Meyer-Scott: Panel Sample Project Management

Physical measures, SAQ, SSA, Logging

Esther Ullman:          Panel Sample Project Management

Tracking, MBB confirmation, baseline Iw

Molly Tamulevich:    Project Assistant to both New Sample and Panel Sample Teams

Chapter 3:  Production Management

## 3.1:  Sample Management

Production Coordinators are responsible for making final sample assignment decisions but will call upon Team Leaders to assist.

The size and complexity of the study will require thorough coordination and planning when determining sample assignments. Considerations that will influence decisions include both the geographic location of the sample/interviewer and the capability and efficiency of the interviewer based on previous experience.

The Screening Team will receive sample in replicates with approximately 25% of the sample (4,000 lines) released in the first replicate.

Production monitoring on the Main Team will present many challenges this wave.  Aside from the panel sample, new sample will be spawned over from the screening team on a flow basis and the 2004 MBBs must be confirmed and/or tracked and interviewed as well. This will require keeping a very close eye on several facets of the sample.  To further focus efforts, sample will be released according to priority levels.

Given the complexities of data collection this wave, special reports will be run and distributed to provide supervisors with production statistics beyond what WebTrak alone will tell us.

Some of the key areas that will involve intense oversight for both the Screening and the Main teams include:

      - Putting full effort on priority #1 sample

      - Utilizing successful contact strategies

      - Monitoring completion rates by PSU by interviewer

      - Monitoring DRI consent rates

      - Getting complete and accurate contact information

      - Monitoring PM/Bio consent rates (Main Team)

## 3.2:  Production Goals

Overall Production Goals are shown below. The field staff will receive production goals for the first six weeks of data collection along with a graph illustrating the overall goals for the project.  Adjustments may be made after the results of the first six weeks are known; at which point the next set of weekly goals will go out to the field.

| Week | Wk Ending Date | New (OS) Goal (based on 16,500 lines at 1.5 hours per screener) | Panel Iws- Goal (based on 17,500 Iws) | MBB Confirmations | MBB Iws-Goal (based on 4000) | OS Iws (Based on 3,000 new Iws) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 3/6/2009 | 366 |  |  |  |  |
| 2 | 3/13/2010 | 917 | 450 | 115 | 30 | 15 |
| 3 | 3/20/2010 | 917 | 375 | 0 | 75 | 30 |
| 4 | 3/27/2010 | 917 | 375 | 500 | 75 | 30 |
| 5 | 4/3/2010 | 700 | 270 | 350 | 40 | 15 |
| 6 | 4/10/2010 | 700 | 270 | 350 | 40 | 15 |
| 7 | 4/17/2010 | 917 | 350 | 400 | 75 | 30 |
| 8 | 4/24/2010 | 917 | 350 | 400 | 75 | 30 |
| 9 | 5/1/2010 | 917 | 350 | 400 | 75 | 30 |
| 10 | 5/8/2010 | 917 | 350 | 400 | 75 | 30 |
| 11 | 5/15/2010 | 917 | 350 | 350 | 75 | 45 |
| 12 | 5/22/2010 | 917 | 300 | 325 | 65 | 45 |
| 13 | 5/29/2010 | 700 | 250 | 160 | 50 | 30 |
| 14 | 6/5/2010 | 700 | 250 |  | 70 | 80 |
| 15 | 6/12/2010 | 917 | 350 |  | 70 | 50 |
| 16 | 6/19/2010 | 917 | 350 |  | 70 | 50 |
| 17 | 6/26/2010 | 900 | 325 |  | 80 | 55 |
| 18 | 7/3/2010 | 700 | 300 |  | 70 | 45 |
| 19 | 7/10/2010 | 700 | 300 |  | 70 | 45 |
| 20 | 7/17/2010 | 800 | 425 |  | 100 | 70 |
| 21 | 7/24/2010 | 513 | 425 |  | 100 | 70 |
| 22 | 7/31/2010 |  | 426 |  | 100 | 70 |
| 23 | 8/7/2010 |  | 425 |  | 100 | 70 |
| 24 | 8/14/2010 |  | 425 |  | 100 | 70 |
| 25 | 8/21/2010 |  | 425 |  | 100 | 70 |
| 26 | 8/28/2010 |  | 400 |  | 70 | 70 |
| 27 | 9/4/2010 |  | 400 |  | 50 | 40 |
| 28 | 9/11/2010 |  | 400 |  | 50 | 40 |
| 29 | 9/18/2010 |  | 400 |  | 60 | 70 |
| 30 | 9/25/2010 |  | 450 |  | 80 | 70 |
| 31 | 10/2/2010 |  | 425 |  | 80 | 70 |
| 32 | 10/9/2010 |  | 425 |  | 80 | 70 |
| 33 | 10/16/2010 |  | 425 |  | 80 | 85 |
| 34 | 10/23/2010 |  | 425 |  | 90 | 85 |
| 35 | 10/30/2010 |  | 425 |  | 90 | 75 |
| 36 | 11/6/2010 |  | 350 |  | 90 | 75 |
| 37 | 11/13/2010 |  | 350 |  | 90 | 75 |
| 38 | 11/20/2010 |  | 300 |  | 90 | 75 |
| 39 | 11/27/2010 |  | 200 |  | 50 | 60 |
| 40 | 12/4/2010 |  | 250 |  | 90 | 80 |
| 41 | 12/11/2010 |  | 300 |  | 90 | 80 |
| 42 | 12/18/2010 |  | 300 |  | 90 | 80 |
| 43 | 12/25/2010 |  | 175 |  | 50 | 45 |
| 44 | 1/1/2011 |  | 175 |  | 50 | 45 |
| 45 | 1/8/2011 |  | 300 |  | 90 | 70 |
| 46 | 1/15/2011 |  | 275 |  | 90 | 70 |
| 47 | 1/22/2011 |  | 250 |  | 90 | 70 |
| 48 | 1/29/2011 |  | 250 |  | 90 | 70 |
| 49 | 2/5/2011 |  | 275 |  | 80 | 60 |
| 50 | 2/12/2011 |  | 225 |  | 80 | 60 |
| 51 | 2/19/2011 |  | 225 |  | 70 | 50 |
| 52 | 2/26/2011 |  | 200 |  | 70 | 50 |
| 53 | 3/5/2011 |  | 150 |  | 65 | 45 |
| 54 | 3/12/2011 |  | 150 |  | 40 | 35 |
| 55 | 3/19/2011 |  | 100 |  | 30 | 30 |
| 56 | 3/26/2011 |  | 59 |  | 5 | 10 |
|  |  | 16500 | 17500 | 3750 | 4000 | 3000 |

HPI Goals

| Mode | HPI |
| --- | --- |
| FtF-E | 8.0 |
| FtF | 6.5 |
| TEL | 5.0 |
| New Sample FtF-E | 9.0 |
| New Sample FtF | 7.5 |
| Completed Screening line | 1.5 |

Response Rate Goals

| Sample Type | Response Rates |
| --- | --- |
| Re-Iw | 95% |
| Re-Con | 32% |
| New Sample | 75% |

Production Coordinators, with assistance from Team Leaders, will manage the production goals and expectations for their assigned work teams. The oversight responsibilities include:

- Production interview/screening goals

- Efficiency expectations (HPI/HPS)

- Level of weekly effort (meeting the projects’ hourly interviewer commitment)

- Follow-up responsibilities

- Quality expectations

- Administrative requirements (Tenrox, ST tasks, email, etc.)

As a Team Leader, you are the person working directly with the interviewers on a daily basis and will be responsible for managing the workload of your team. You must clearly review production expectations with each interviewer and assess situations where these expectations are not being met. For example:

- Are they  meeting the required minimum 25 hours per week

- Are they working within the expected HPI/HPS guidelines

- Are they submitting the required mailings each week

- Are they meeting quality expectations

- Are they completing all administration tasks in an accurate and timely manner

- Are they displaying a professional manner

- Are they meeting communication expectations

The first three weeks of production is the most critical time for evaluating performance.  It is during this period of time that work habits are established.  You should be monitoring reports as often as possible during these initial weeks of production.

Interviewers must meet the requirements outlined in the Employee Commitment Statement, which they all signed prior to production. You should refer to this document when having conversations on expectations with your interviewers. (Refer to Appendix ?: Employee Commitment Statements)

While identifying areas of concern is critical to monitoring production, it is equally important to provide the necessary tools and supportive environment to help your team succeed. This is where appropriate feedback along with effective guidance comes into play.

In keeping with the SRO philosophy, providing a work environment that is not only supportive but one in which everyone is given the opportunity to succeed and to grow is vital to the success of  HRS and to the SRO organization overall. Accomplishments must be recognized, guidance must be provided as needed and the lines of communication must be open, respectful and available to all.

The mentor plan which began in 2008 will continue this wave of HRS and is intended to help us achieve the goal of building and retaining a team of successful and satisfied employees.

## 3.3:  Handling Performance Concerns

Step 1

In most cases, the first course of action will be for the Team Leader or Production Coordinator to guide the interviewer and to offer additional help as needed.

The TL, PC or PM will verbally inform the interviewer of the number of interviews they have completed; any quality issues (i.e. evaluation results,) the number of hours they have worked and/or their HPI and reminded him/her of the study goals.  During this time, the TL or PC should also outline the ways in which the interviewer can begin to meet the expectations and provide him/her with a plan for follow-up, etc. This may also be the time to discuss the opportunity to work with a peer (mentor).

  - The facts are stated without mention of consequences or repercussions. Interviewers that reach the study goals within the allotted review period are to be congratulated on their success.

  - Interviewers that improve performance to an acceptable level as determined by the Production Manager, but not yet reaching the study goals, will be counseled by the PC or PM and new goals (with a new review period) will be set.  The interviewer will be informed that failure to meet goal could result in the transfer of sample and/or no new sample assignments. Again, this is a time to provide strategies to help the interviewer succeed in meeting the goals..

  - Interviewers that show little or no improvement will move to step 2.

  - All verbal conversations must be documented and sent to the PC and PM. Additionally, a follow-up email restating the points covered in the discussion should be sent to the interviewer (with a cc to the PC and PM) directly after the conversation.

Step 2

The TL or PC will send the interviewer an email, using the provided template, outlining the number of interviews they have completed, any quality issues, the number of hours they have worked and/or their HPI along with the study goals.  A specific plan for improving performance will be outlined and a timeline for meeting these expectations will be provided.  The PC and the Production Manager will be copied on this email.

- Interviewers that reach the study goals within (the allotted

review period) a week will be congratulated on their success.

- Interviewers that improve performance to an acceptable level as determined by the Production Manager, but not yet reaching the study goals, will be counseled by PC or PM and new goals (with a new review period) will be set.  The interviewer will be informed that failure to meet goal could result in the transfer of sample and/or no new sample assignments.

- Interviewers that show little or no improvement will move to step 3.

Step 3

Interviewer will receive a written warning from the Production Manager in format approved by Human Resources.  Data Collection Services, the TL and the PC will receive a copy.

  - Interviewers that reach the study goals within (the allotted review period) will be congratulated on their success.

  - Interviewers that improve performance to an acceptable level as determined by the Production Manager, but not yet reaching the study goals, will be counseled by PC or PM and new goals (with a new review period) will be set.  The interviewer will be informed that failure to meet goal could result in the transfer of sample and/or no new sample assignments.

  - Interviewers that show little or no improvement may be removed from the project by the Production Manager.

See the sample template below:

From:  Team Leader or Production Coordinator

To: Interviewer

CC: Team Leader; Production Coordinator; Production Manager

Subject:  Goals and Expectations

Interviewer,

You have (completed X interviews) (worked X hours in the last X weeks) (an HPI of X.)

The study (goal) (commitment) is (X interviews a week) (X hours a week) (goal HPI.)

To reach the study (goal) (commitment) you need to (complete X interviews) (work X hours) (complete X interviews in X hours) by XX/XX/2005.  As we have discussed, it will help you reach this goal to (work evenings) (work weekends) (reduce admin time by faxing Tenrox) etc.

We believe these goals are realistic and are looking forward to your success.  Please let us know if you do not believe you can reach these goals or if there is anything else we can do to help.

## 3.4:   Documentation (Employee Activity Report)

Documentation must be maintained.  PCs are responsible for providing the PM with the initial document outlining the series of events, conversations, email messages, etc.; which should be in date order. The PM will add additional details to the document before sending on to DCO for the records and review.  The document should include the following details:

- Date of event(s)

- Date(s) and details of all communications with the interviewer (include copies of any written communication(s) in an appendix

- Follow-up actions taken by TL/PC/PM

- Details of the strategies offered

- Performance improvement results (must include production details)

## 3.5:   Reporting Illness/Injury/Theft or Adverse Events

Illness/Injury Report Form

If an interviewer is injured or becomes ill while on the job, the incident must be reported to the PM within 24 hours. The PM then submits the report to DCS.  The same template is to be used if there is an incident of theft or auto accident.

If you are unsure if an event should be reported, contact Dianne Casey or Sarah Crane to review the details.

Adverse Events Report Form

This form was created to provide us with a means of reporting events other than interviewer related illness, injury or theft. The report should go directly to the production/project managers within 24 hours of the event.  And rather than forwarding this report on to DCS it stays at the project level. The project would then make a decision if the incident report should be escalated to IRB as well.

Examples of these potential events are as follows:

- A respondent becomes ill or injured during the interview

- The interviewer witnesses disturbing or inappropriate behavior

- Confidential material is lost or accidentally left in respondent’s home

(See templates in appendix A).

## 3.6:   Clinical Contact Portal

The Survey Research Center is committed to providing support to respondents and to interviewers.  We understand that the job of the interviewer involves interacting with respondents in our studies.  Sometimes the questions we ask can themselves stir up feelings in both the respondents and the interviewers. During in-person interviews, field staff witness what goes on in the homes of real people in their daily lives.

We have established specific protocols to help interviewers handle some of the things that can occur.  The most important thing for an interviewer to know is that you have the solid support of the University of Michigan, Survey Research Center.  You are not expected to handle these issues alone.  We will outline the protocol for handling the type of situations that you may encounter:  1) emergencies; 2) distressed respondents; 3) reporting unusual situations or possible abuse; and 4) getting help for yourself.

Emergencies

When interviewing in a respondent’s home, you may observe a situation which warrants immediate action on your part.  Though very rare, should you ever witness a violent crime, a child or anyone else in immediate danger, or other similar situation where not calling the local police or fire department would endanger the lives of the people living in the respondent’s household, call the local authorities immediately.

As soon as possible after you have done this, please contact your Production Manager. If you cannot immediately reach her, please call the SRO toll-free number (1-800-759-7947) and ask to speak with your project leader. If he or she is not available, please ask to speak with one of the members of the Survey Research Operations (SRO) management team.

It is highly unlikely that you will ever be involved in such a situation.  If there is any ambiguity about the severity of the situation, please call your Production Manager first, before taking any action.  We want to protect the privacy of the respondents and members of their households, but not at the cost of the safety of the family.

After you have reported the situation to someone at SRO, you should speak with someone from the Clinical Contact Team.  Please call the SRO toll-free number and say that you have an emergency and need to speak to the CC Team.

Distressed Respondents

Sometimes when a questionnaire includes sensitive topics, some respondents may experience distress during or after an interview.  You should familiarize yourself with this protocol so that you are comfortable handling these types of situations:

First, you should never try to advise the respondent.  If they are too upset to continue the interview, you should take the following steps:

Tell the respondent something like this:  “I am sorry that you are upset.  I’ll wait until you are ready to continue.”  If he or she is crying, you may wish to offer a piece of Kleenex or ask if he or she wants to get a drink of water.  Give the respondents ample time to compose themselves.

If the respondent is not able proceed after a few minutes or if they ask you for help, you should say “I’m not trained to help you with this situation, but the University has help available for you. We have someone associated with our study who is specifically available for this purpose.  Would you like me to have that person give you a call?  She will contact you soon and talk to you and if you need further help, she will help you find a resource in your area.”

In the very rare situations where the respondent mentions that they are thinking of hurting themselves or others, you must contact someone from the Clinical Contact team.  You can either tell the respondent that you plan to do so, or not, as you see fit.  If the threat of suicide is immediate, contact 9-1-1 first.  (This is highly unlikely.  We mention it here only so that you will know what to do if it ever does occur.)

If the respondent is able, make an appointment to complete the interview at a later time. If not, let him or her know you’ll follow up in a few days.

The next step is to immediately contact the Clinical Contact (CC) Team.  See the process for contacting them below.

In cases where the respondent shows some distress, but is able to continue with the interview, you still may offer this service to them at the end of the interview.

You may contact the CC Team about a respondent even if you did not talk about this possibility with the respondent.  Sometimes you may not be fully aware of your concern about a respondent until a day or two after the interview.  All members of the CC Team have signed the ISR Pledge of Confidentiality and are bound by it.

CONTACTING THE CLINICAL CONTACT TEAM:

In most cases, the best way to contact the team is by sending an email to their group address (SRO-CCP@isr.umich.edu).  This email should contain a summary paragraph describing the situation (do not include any respondent identifying information), the best time and phone to reach you (as well as your time zone).  You should also include any suggestions you may have about the best time to reach the respondent and the respondent’s time zone, if that is relevant to the situation.  A CC Team member will contact you to follow-up.  In some cases, you may feel like the situation is more urgent and that you need to speak to someone right away.  If so, call the 800-line (1-800-759-7947).  They will contact the CC Team member on call and someone will call you back as soon as they can.  If you do call, you should still send the CC Team an email as described above, being sure to mention that you have asked for a call back.

Reporting Possible Abuse

There may be times when you are at a respondent’s house that you may observe physical abuse or neglect of someone in the household, or you may be told of such abuse.  These situations can be very upsetting.  If you feel or even suspect that you have observed abuse, you should report it by following the same procedure as above.

Getting Help for Yourself

It is possible that at times you may feel upset yourself after conducting an interview with a respondent who is distressed. If you feel you need to talk to someone about your feelings related to that type of situation, you should also follow the procedure above to contact the CC Team.

In addition, if you yourself need assistance in handling any relationship, emotional or work-related, there is another UM resource available to you.  The Faculty and Staff Assistance Program (FASAP) is available to you as a University employee.  FASAP brochures will be distributed at interviewer training during registration.  To schedule an appointment for counseling, you may contact FASAP at 1-734-936-8660 (this is not a free call) or you may email them at fasap@umich.edu.  For more information about services available at FASAP, see their website:  http://www.umich.edu/~fasap/.

We are pleased that FASAP is providing short term counseling and referral services to our interviewing staff that may encounter difficult or troubling situations. The service is strictly confidential and FASAP does not provide us with any individual or demographic information on who has used the services, though they will be giving us aggregate data as to how many of our interviewers have utilized the service

## 3.7:  Team Meetings

Maintaining close communication with your assigned interviewers is vital in building an effective working rapport with your team. This also assures them that you are there to assist in building production strategies as well as recognizing their accomplishments.

Each week, you and your Production Coordinator will conduct a conference call team meeting with your interviewers. These generally last one hour, where attendance is mandatory. Facilitation may shift between the PC and TL each week.

Having interviewers actively participate is crucial in building a self-motivated team who feel connected and recognized.  Asking interviewers to present a topic on the agenda or to share in the facilitation will go a long way in promoting active participation.

Standard agenda items will remain the same for all work teams and a standard format will be developed.  Following are some of the basic facilitation rules that an effective facilitator should keep in mind.

- Encourage members to participate

- Assist the group in finding win/win solutions

- Protect members from attack

- Keep the group focused in the meeting task (start and end on time)

*Remember-it’s never appropriate to make a negative comment on individual performance in a group meeting.

In addition to these weekly team conference call meetings, you will hold an individual meeting with each of your team members on a predetermined schedule. These meetings are often called mid-week reports and are intended to give you and the interviewer an opportunity to discuss individual production/quality results and to determine appropriate strategies for the week ahead.

## 3.8:  Team Production Reports

Production reports are gathered from all interviewers and incorporated into a master file in eRoom each week.  You are responsible for collecting these reports via email attachments and/or during the weekly team conference calls.  After you collect the production report data, you’ll need to update the master file in eRoom.  Your PC will then incorporate each TL report into the master file representing the entire PC work group. Your PC will then summarize the data in a text report and will include some anecdotal information such as respondent reactions to different components of the IW, personnel issues, stories from the field, travel plans, etc.

(Refer to Appendix ?: Reports for 3 exhibits of report files: Report Chart.xls, Iwer Report Chart.xls and Text Report Template.doc).

## 3.9:  National Tracking Team (NTT)

A valuable resource for the tracking efforts is found in the National Tracking Team. It consists of six members across the country, in addition to a Project Manager in Ann Arbor and a field Task Team Leader. Among their many responsibilities is to monitor all tracking cases in their workgroups to assist in early identification and locating lost respondents. They ask the TL to help with this by monitoring WebTrak 6th call no contact flags for any possible tracking cases and reviewing the call record to determine if the case should be in tracking.  Using this and the tracking report, NTT will work with each individual interviewer on one-by-one calls if needed. Internet searches will be done, and they will also coordinate transfer of tracking cases to the NTT or to a nearest available face-to-face interviewer. Towards the end of production, the NTT and Task Team Leader will also make determinations of final code out of lost this wave.

A TL should be prepared to encourage their Interviewers to contact the NTT member when they discover their first tracking case. Also, when reviewing the interviewer call records and the 6th flag report, alert the interviewer and NTT if there are any cases that should be in tracking. By stressing good call notes and reviewing that all information is entered correctly in the view/edit screens, TLs will greatly increase the efficiency of tracking this wave and in future waves. Additionally, TLs should help NTT to identify good trackers as well as those who may need retraining. And finally, include the NTT member and tracking issues on all team conference calls to assure success.

## 3.10:  WebTrak (WT)

WebTrak is designed to capture SurveyTrak data, which allows authorized users to monitor all the necessary phases of data collection and production stats. This is where you will review call records, field progress reports and evaluation/verification results. It is important that you become familiar (and comfortable) with the functions of WT so that you can identify potential problem areas.

The printable reports include but are not limited to the following reports:

- Field Progress Report-Counts: This report summarizes the current status of the sample lines in the project., both overall as well as by subgroups such as PC, TL, cohort, instrument type, etc.

- Field Progress Report-Rates:  The data in this report reflects the current project rates (as percentages) including response, completion, Spanish, telephone, refusal conversion rates, etc.

- Cost Report: The breakdown of hours, miles and expenses are displayed at the project level as well as the interviewer level

- Evaluation/Verification Report:  This report reflects current stats on all completed as well as pending interview evaluations and verifications.

- Tracking Report:  This report monitors all SIDs assigned to a tracking result code

Additional reports include the compliance, logging and follow-up reports.

(Refer to Appendix ?: WebTrak Manual)

## 3.11:  eRoom

eRoom is a web-based program, which allows authorized users to maintain and share documents.  It enables the author of the document(s) to grant edit rights to those who may need to update the data. One of the major benefits of eRoom is the ability to have several people view a document at the same time while only one person can edit the document at one time. By maintaining only one version, the danger of having someone refer to an outdated document is eliminated.

The HRS 2010 eRoom will be used to store weekly production report files as well as reference material that will be used throughout data collection. Your PC may instruct you on specific work group documents to be stored in eRoom as well.

## 3.12:  Staff Lists/Updates

At the beginning of data collection, Tina Schneider (from the Front Desk in Ann Arbor) will be provided with the HRS staff list, along with contact information. This enables the person answering the respondent 800# to quickly identify the interviewer’s TL when forwarding information relating to the respondent call. Additionally, Tina uses the contact information to forward calls directly to the appropriate iwer. Therefore, it is imperative that any and all changes are reported to Tina as they occur. PCs are responsible for communicating these changes directly to Tina via email.

## 3.13:  Interviewer Travel

As in past waves, HRS will utilize travelers when needed. Cecilia Waguespack will fill the role of Travel Coordinator this wave.  Helen Stone will assist Cecilia as needed.  Utilizing a Travel Coordinator will ensure that travel plans are made according to SRO guidelines and allow us to monitor all overnight travel costs closely. Their expertise will help guide interviewers in planning efficient trips, including identifying possible hotels that meet the expected guidelines.  Cecilia or Helen will submit the details of the trip, and the estimated costs, to Dianne Casey or Sarah Crane for final approval.

The first step in arranging travel must be a conversation between the interviewer and you, the Team Leader. Determine if, and when, the trip should take place, the duration of the trip and the estimated number of SIDs that will be worked during the trip. Once this has been discussed, you will need to inform Cecilia that the interviewer will be contacting her to discuss the plan. Cecilia will then investigate appropriate hotels, and assist in arranging air/rental car reservations, etc.

Interviewers will be provided with a Data Collection Services (DCS) handbook (Interviewer Traveler’s Passport) prior to the start of production.  This was created by DCS to assist the interviewer in planning travel.

Interviewers on travel status will be required to submit a travel report each week.  Both the TL and Cecilia will collect these reports, which will be incorporated into a master travel report at the project level. Travelers will be paid a $2.00 differential for trips consisting of two or more overnight stays.

Note that while overtime is not typically approved, it is often approved, with prior notification, for interviewers on travel. This should ultimately maximize production and contain overall travel costs.

## 3.14:  Performance Assessment Form (PAF)

Over the course of data collection, you will complete three Performance Assessment Forms for each member of your team. These will be reviewed first by your PC and then by Sarah/Dianne for final approval before sending on to the interviewer.  Only standard pre-determined comments will be used on these assessments. You will be provided with a list of approved comments to choose from, which will reflect the desired performance feedback. (PAF is currently under construction)

Production statistics as well as quality and other observations such as team work, and administrative tasks completed that you have noted throughout the review period will be used as the basis for these assessments.

The first PAF is to be completed by June 30th. The second one is due by Oct. 30th. The final PAF should be completed by Feb. 30th (or when then interviewer completes his/her assignment).

## 3.15:  Approving Time and Expenses in Tenrox

An important part of your job as a Team Leader is to review and approve time and expenses each week in Tenrox. Timesheets should be approved by Monday morning each week. Expense reports should be approved as they are submitted, on a flow basis. When reviewing timesheets, pay particular attention to how the interviewer is reporting his/her time within each work type. The following guidelines should apply.

Main Data Collection- Administration

Simply defined, this study phase code includes all time you spend on the project that does not directly involve data collection.  This may include time spent in meetings with your supervisor, participating in conference calls, completing your weekly report, entering your time in Tenrox, packing and mailing materials back to the Ann Arbor office, Sending and Receiving in SurveyTrak, checking and responding to email, sending pre-contact letters, requesting persuasion letters, transferring sample, and doing post office errands and/or office supply errands (but not the travel to and from the post office or office supply location).

Main Data Collection- Computer Problems

Includes time spent working with Helpdesk on specific software/hardware computer problems

Main Data Collection- Production

Production includes only time spent conducting the actual interview with a respondent, completing interviewer observations, calling for appointments and entering call records into the computer.

Main Data Collection- QC/Validation

Includes time spent reviewing interview evaluations and verification results with your team members.

Main Data Collection- Travel

Travel time includes any time you spend traveling in your car, by plane, bus, subway, bike or foot while engaged in work for this project.  You should include time spent traveling to the post office to mail materials back to the office as well as the time spent traveling to an interview.  Sometimes, your travel time will include overnight travel to complete an interview rather than just a short trip.  In the case of overnight travel, you should include only the time spent actually traveling and not the time you spend contacting the respondent to confirm the appointment or time spent completing the interview.

Main Data Collection- Tracking

This work type is to be used by members of the NTT and will include time spent conducting tracking activities, monitoring tracking the efforts of assigned interviewers, joining tracking team calls and communicating tracking issues.

Another tool you’ll use to monitor time and costs is the WebTrak cost report.  This is where you’ll determine possible outliers. For example, you may notice that an interviewer is charging 50% of his/her time to administrative tasks while the average may be closer to 35%. Or, you may determine that an interviewer has excessive time or costs charged to travel or mileage.

During data collection in 2008, interviewers spent an average of 20% of their time on administrative tasks; which is a key indicator of how efficient an interviewer is working. This 20% average should be used as a gauge for 2010.

If you feel the time and/or expenses reported are not accurate or in question, you should gather more information from the interviewer and discuss the matter with your PC before approving or rejecting the timesheet or expense report.

Refer to the Supervisory Supplement to the Tenrox Manual (Refer to Appendix A: Tenrox Instructions) for instructions on how to navigate in Tenrox as a Team Leader.

## 3.16:  Interviewer Supplies

Interviewers are responsible for ordering supplies from the Interviewer supply email (iwersup@isr.umich.edu) as needed. However, they are required to CC you, the TL, on the email request.  It is important for you to review all such requests and step in if you feel that the request is unnecessary.  For example, an interviewer may request UM franked envelopes but you may be aware of an interviewer who has an excess number on hand and could simply mail those to his/her colleague.

________________________________________________________________________

Chapter 4:  Project Supervision

## 4.1:  Interview Mode

The assigned interview mode must be adhered to unless there is a valid reason for change. Some examples of valid reasons are listed below:

- A respondent assigned to telephone mode has difficulty hearing over the phone

- A respondent assigned to FTF mode has refused but will agree to the interview if completed over the phone

- A respondent assigned to telephone mode is now institutionalized, which would require a FTF interview this wave

- A respondent assigned to telephone mode is reluctant. The interviewer feels that going FTF would offer a better chance of conversion

When it is necessary to alter the mode of interview for a respondent, interviewers must obtain prior approval and document the reason in the Interviewer Observations section of SurveyTrak as well as in the call notes.

Interviewers do not need prior approval for mode changes (FTF to TEL) in cases where the respondent is deceased and we now have to collect an Exit Interview.

TLs may approve mode changes for respondents who report having difficulty hearing over the phone.

PC approval is required for all other mode change requests.

## 4.2:  Proxy Interviews

It is always preferable to do an interview with the respondent him/herself.  Unless Respondent Profile information clearly indicates that the respondent has a permanent impairment which would prevent him or her from completing an interview or granting permission to contact a proxy reporter, Interviewers should always attempt to contact him or her first.

It is possible that the situation of respondents who were unable to complete their own interviews last wave will have improved to the point that a Self or Assisted Self Interview will now be possible.

While the most common reason for taking a proxy interview is that the respondent is physically or mentally impaired to such a degree that he or she cannot complete a self-interview this wave, there are other valid reasons as well. For example, a respondent may refuse a self-interview but grants permission for his/her spouse to do the proxy interview on their behalf.

All proxy interviews must have prior permission from the respondent. Only in extreme cases of impairment is it appropriate to conduct an interview with a proxy reported without first having the respondent’s permission.

The interviewer must first discuss the situation with you. You will then bring the request to your PC’s attention for final approval before instructing the interviewer to proceed.

## 4.4.:  Respondent Types (Change Requests)

It is important to keep the reporter of information consistent from wave to wave. There are, however, rare instances where the assigned R-type assignment should be changed. For example, if the Interviewer feels that he/she will not be able to get the second interview and it may be difficult to get the available respondent to do a proxy for the spouse, the R type of the first respondent should be changed to Fin/Fam. Likewise, if pre-interview conversations with the respondent or the respondent’s spouse lead you to believe that the Fin R may no longer be the person most knowledgeable about the household’s financial status, you should consider changing the respondent type.

If an Interviewer identifies a case that may warrant a change in R-type designation they should attempt to talk with their Team Leader prior to changing the respondent type. If you have any doubts, discuss the particulars with your PC. The reason for changing the Fin/Fam designation should be documented in the call record.

## 4.5:  Respondent Profiles

The respondent profile is an important tool to use when building contact strategies. Interviewers should always review the respondent profile prior to initiating contact with a respondent. Getting your interviewers into the habit of thoroughly reviewing the profile prior to the first contact attempt will maximize the chances of a successful contact on the first attempt. Additionally, when an interviewer comes to you to discuss a specific case, be sure to review the details of the profile together. You may glean something that the interviewer missed the first time. There is a wealth of information in the profile. Using it will help you and the interviewer to build effective strategies.

The screening sample will have a similar tool; called Related Case Details and is accessed the same way you would open a profile (from the SurveyTrak drop down list).  These will include the segment and household OBs from the listing that was completed in 2003 and 2009.

## 4.6:  Rules for Removing from Sample

In rare instances, specific refusals may be removed from the sample. For example, if the respondent threatens legal action or has called or written to Ann Arbor with explicit instructions not to contact the household again, the project staff may decide to remove them from the sample. If an interviewer comes to you with a situation that may warrant this recommendation, review the details with the interviewer. Then you will need to bring the case to your PC for further review. After the PC reviews the case, she will forward the recommendation on to Ann Arbor. Project staff will make the final decision and will notify the PC and TL.

## 4.7:  Call Records/Result codes

In reviewing call records, you are able to determine a variety of things. They will tell you whether the interviewer has attempted contact during appropriate (and varied) days and times, if the details provided in the call notes are complete and appropriate and whether or not the correct result codes are being used.

Keep in mind that Interviewers should not assign final result codes without prior permission from his/her PC.

Reviewing a random selection of call records each week is an important part of your job as a Team Leader.

As part of the training materials, Interviewers were provided with a document titled “Points to Include in Call Notes”.  They are also provided with a copy of the result codes on cardstock.  You should keep these on hand to assist you in your weekly call record review.

Keep a running list of observations that you’ve made (based on these reviews). This should be one of the items you’ll cover with your interviewers on the individual weekly calls. Keep in mind that you should recognize excellent call records as well as commenting on areas needing improvement during these conversations.

## 4.8:  Sample Transfers

WebTrak, and other production reports, provide you with an overview of the status of cases.  It is important that you monitor the progress of your team on a daily basis to determine whether interviewers have too many cases that are not being worked, if they have too few cases, or if they are not working effectively.

You should also look closely at the resistant cases. In some situations, it may be more productive to transfer to a more experienced interviewer, an interviewer who is local and could make a FTF attempt or to an interviewer of the same gender as the reluctant respondent.

There are a variety of reasons why you may recommend transferring sample. And, in some cases, you may identify sample that should be transferred to interviewers in another work group. In these situations, you will need to inform your PC of the details, who will then discuss it further with the PC from the appropriate workgroup.

## 4.9:  Quality Plan

### Evaluation Plan for HRS 2010

Five to 10% of all completed interviews will be recorded. These interviews will be sent to the Ann Arbor centralized QC team on a CD for evaluation.

SRC standard evaluations will be used for HRS.  Evaluators in Ann Arbor will complete a thorough review of recorded interviews through simultaneously listening to the interview. Evaluators will complete the WebTrak evaluation form as soon as the evaluation is completed.

The following steps will take place:

- Receipt of the recorded interview will be documented in WebTrak. When interviewers next send/receive, receipt of the iw will appear as updated on the “CD” or "Tapes" tab in SurveyTrak. If a recorded interview is not received in Ann Arbor within two weeks of the date it was sent, TLs should promptly contact the interviewer to follow-up on the recording. Recorded interviews not received in Ann Arbor are considered a breach of confidentiality and must be reported to the IRB.

- Evaluations should be completed within one week of receipt.

- The electronic evaluation form completed in WebTrak can be saved by pressing a SAVE TO WEBTRAK button at the bottom of the form.  Once the evaluation is complete and the SAVE TO WEBTRAK button is pressed, the data will be recorded in WebTrak and the WebTrak screen will display the word "Done."  Team Leaders will then be able to view the evaluation results but will not be able to edit them.

- Once Team Leaders have reviewed the evaluation results, they will be able to press a “Save/Email to Iwer” button to forward the evaluation to the interviewer via email.  Once the evaluation has been forwarded to the interviewer, WebTrak will display “Sent” in the evaluation column.

- Evaluations will not be editable once saved by the evaluation staff; however, TLs, PCs, and other reviewers will be able to add to the “Additional Notes” field of the WebTrak evaluation screen.  A history of all comments will be saved in this field.

The evaluation effort will be managed jointly by the Central QC Coordinator, LaVelvet Harrison, the Field QC Coordinator, Sarah Crane.

### Verification Plan for HRS 2008

Flagging Rules

Each HRS interviewer will have his/her first two completed interviews/NERs verified. WebTrak will automatically flag the first two completed interviews.  Ten percent of each interviewer’s completed interviews/NERs thereafter will be randomly and automatically flagged and verified throughout the course of production.  Flagging occurs daily.

General Information

- Verifications will be conducted centrally in Ann Arbor.  Verifications must be conducted promptly after the interview has been completed.

- Depending on whether contact is made with a respondent or informant in the household, an appropriate number of verification calls made at different call windows should be completed within two weeks of the interview being flagged.  If verification is not able to be completed after the appropriate number of calls the line should be coded “Unable to Verify.”

- If there is no contact with an informant or respondent in the household, make a maximum of 10 calls to the household.

- If there is contact with an informant or respondent in the household, make a maximum of 20 calls to the household.

- If a line is coded “Unable to Verify,” the verifier should manually flag a different completed line by the same interviewer for verification.

- Verifiers should use a script when calling households.  The script should identify the verifier and explain why they are calling.

- The Central QC Coordinator, Field QC Coordinator, Production Coordinators, Team Leaders, and Project Managers will review the WebTrak verification reports on a weekly basis and have the opportunity to review completed verification questionnaires on WebTrak.

- In addition to several general questions, a small group of variables from the Main 2010 instrument will be selected for verification.  This will allow us to verify the legitimacy of the data entered.  WebTrak will display the answers to the specific variables from the Blaise interview on the verification screen.

- WebTrak will allow the verifier to enter the answers to the verification questions in WebTrak beside the interview responses to each question.  WebTrak will also allow the verifier to indicate whether each question was verified as well as whether the interview as a whole was verified (please see the attached verification questionnaire specifications).

- The verification effort will be managed jointly by the Central QC Coordinator and the Field QC Coordinator.  A Project Manager will oversee and consult on verification.

Verification Codes and Definitions

These verification codes and definitions were established in order to ensure consistency among all verifiers.

The verifier will probe the respondent/informant in order to reconcile any discrepancies and record these probes in Verification Outcome "details" section.  The verifier has the authority to recommend whether or not the case should be accepted as verified.  The codes are noted in parentheses.

The verification outcome code definitions are listed below.

Code Definitions

| FLAGGED | (1) | Flagged for verification. |
| --- | --- | --- |
| VERIFIED | (2) | All verification data match CAI data OR there is one piece of verification data that does not match CAI data. |
| VERIFIED WITH DISCREPANCY | (3) | Two pieces of verification data do not match CAI data. |
| FAILS VERIFICATION | (4) | More than two pieces of verification data do not match CAI data and the verifier's overall judgment about the interview indicates a failure. |
| UNABLE TO VERIFY | (5) | Respondent or informant is contacted but is unwilling to participate in verification exercise OR the verifier is unable to reach the respondent/informant (including reaching the household by telephone, but not reaching the respondent/informant). |

## 4.10:  HRS Q&A

HRS Q&A is an email box set up to collect questions from the field staff and respondents. This is to be used by PCs as needed. You should, however, go to your PC first with all questions. If your PC is not able to answer the question, the question will either be forwarded to Sarah or Dianne or sent to the HRS Q&A mailbox.

This mailbox is read by Heidi Guyer as well as the Ann Arbor Project Managers. The appropriate person will respond to the PC. Depending on the nature of the question, it may require additional input from the project staff. In some cases, the response may be delayed depending on the amount of background review that needs to take place in order to accurately respond to the question.

## 4.11:  Post Production Activities

As interviewers complete their assignment on HRS, a variety of closeout tasks are in order.  You should instruct them on the return of their laptop, equipment and study materials.  Interviewers will be provided with the detail instructions as indicated below.  As the TL, you’ll need to work closely with your interviewers to assure that they follow these steps once they have completed their HRS assignment.

# When You are Finished Working on a Project

The following close out procedures are in addition to anything your Team Leader or Production Manager requires of you.

When an interviewer terminates or has finished work on a project and will not be assigned to another project in less than 1 month, it is the responsibility of the Production Manager or Team Leader to make arrangements for the return of equipment.

Step 1:  The PM or TL will contact you to coordinate the shipping of the computer.  Final sample reconciliation must be done at this time.

Step 2:  The PM or TL will inform the Help Desk staff that you will be returning the computer and a Help Desk call will be opened.

Step 3:  Ship the computer to Ann Arbor following the provided shipping instructions. It is your responsibility to provide the PM or TL with a valid UPS tracking number.

Step 4:  The PM or TL will inform the Help Desk staff of the valid UPS tracking number and that the computer has been shipped.

Step 5:  Upon receipt of the laptop in Ann Arbor, DCS staff will conduct final check of sample and close out interviewer from all applicable projects.

# Computer Shipping Instructions

# The computer must be in its bag and placed in a box with no less than 2 inches of material (crumpled paper, bubble wrap, Styrofoam peanuts) surrounding it.  For final returns, all computer peripherals should also be placed in the box including but not limited to:  Computer carrying case, computer power supply, DVD/ CD-Rom drive, extension cord, 3-prong adapter, phone cord, telephone duplex adapter, telephone fem-fem adapter, automotive power adapter (if applicable), and extra battery pack (if applicable).

Fill out the UPS shipping document. Whenever possible, use a pre-printed UPS shipping document that has been provided to you for the project which you are working. If you do not have a pre-printed UPS shipping document, fill out a blank document using the following information.

1.	The shipper’s UPS account number is X43440. **

2.	The reference number is the 6-digit Short Code for the project. Your PM or TL will provide you with the 6-digit Short Code for the project. **

3.	The shipping address is:

Mike Etzel

University of Michigan - ISR

330 Packard - B342 Perry Bldg

Ann Arbor, MI 48104-2910

4.	The phone number is 1-800-631-2819.

5.	Fill in the weight of the package.

6.	The insured value should be $2,000.00.

7.	The method of payment is “Bill Shipper”.

8.	Sign and date the document.

**DO NOT ADD ANY ADDITIONAL INFORMATION TO THESE FIELDS OTHER THAN WHAT IS SPECIFIED.

To schedule a pickup with UPS, call the number located at the top of the pre-printed UPS shipping document (1-800-PICKUPS).  Follow the voice prompts. At the main menu select “send a package”, then select “schedule a pickup”. For shipping options, select “Air”. Continue to follow the voice prompts and provide your home telephone number. The voice prompt will provide a pickup charge amount and ask if you have a credit card available to accept and pay the pickup charge. Answer “no”.  Continue to follow the voice prompts and say “agent” to speak to a UPS customer service agent. You will need to provide the UPS account number “X43440” and the UPS account zip code “48104” for the pickup charge to be billed directly to the UPS account. If pickup service is not available in your area and you need to find a UPS pickup location, at the main menu select “send a package”, then select “locations”. Follow the voice prompts and select “full service locations”. Preferred pickup locations are a UPS Customer Center or The UPS Store. Never ship a computer from a UPS Drop Box.

If you have any problems with UPS or with filling out the shipping document, please call the Help Desk at 1-800-631-2819.

Additionally, you should notify Joanne Dopkowski (via email) to cancel the Interviewer’s sprint card and dedicated UM telephone line.